|  |  |  |
| --- | --- | --- |

BT NETWORK INTERCONNECTION PROVISIONING MANUAL

- SECTION 11 – SMS MESSAGES INTERCONNECT

# CONTENTS

CONTENTS	2

11.1	INTRODUCTION	4

11.2	PLANNING THE INITIAL INTERCONNECT	4

11.2.3.1	Initial Technical Planning	4

11.2.3.2	Provision of SMS Messages Interconnect Capacity	5

11.3. CAPACITY PROFILE	6

APPENDIX 31a	6

APPENDIX 31b	6

11.4.	PROVISION OF SS7 MAP SIGNALLING LINK 64Kb/s CAPACITY	7

11.4.1	PROCEDURES AND TASK OVERVIEW	7

11.4.1.1 	Preliminary Planning	7

11.4.1.2	Capacity Profile	7

11.4.1.3	Capacity Orders	7

11.4.1.4	Provision of SS7 MAP Signalling Link 64Kb/s Capacity	8

11.4.1.5	Ready For Test	8

11.4.1.6	Operational Testing	8

11.4.1.7	Bringing Into Service	8

11.4.2	Testing Requirements	9

11.4.2.1	New Switch Testing Requirements	9

11.4.2.2	Time Scales	10

11.4.2.3.	Operational Interconnect Switch Testing	10

11.5	CESSATION  OF SS7 MAP SIGNALLING LINK 64Kb/s CAPACITY	11

11.5.1  PROCEDURES AND TASK OVERVIEW	11

11.5.1.1 	Preliminary Planning	11

11.5.1.2	Orders for the Cessation of SS7 MAP Signalling Link (64Kb/s) Capacity	11

11.5.1.3	Cessation of Capacity	11

11.5 DOCUMENT HISTORY	12

ANNEX A - STAGES AND KEY ACTIVITIES	13

CAPACITY PROFILE PROCEDURE	13

Key Activities - Descriptions	14

ANNEX B - STAGES AND KEY ACTIVITIES	15

PROVISION OF SS7 MAP SIGNALLING LINK 64Kb/s CAPACITY	15

Key Activities - Descriptions	16

ANNEX C - STAGES AND KEY ACTIVITIES	17

CESSATION OF CAPACITY	17

Key Activities - Descriptions	18

## 11.1	INTRODUCTION

This section describes the joint approach, between the OPERATOR and BT, to the planning and provision of the SMS Messages Interconnect between the respective networks.

The principal forum for the initial and ongoing technical and planning discussions between the OPERATOR and BT will be the Technical Review Meeting.

The Technical Review Meeting forms part of the Liaison Structure between the OPERATOR and BT.

## 11.2	PLANNING THE INITIAL INTERCONNECT

SMS Messages Interconnection between the OPERATOR and BT requires careful planning to ensure that the two networks interwork correctly, that customers are provided with the agreed range of services and that neither network causes service problems for the other.

### 11.2.3.1	Initial Technical Planning

The Technical Review Meeting will co-ordinate the initial technical and planning arrangements that culminate in bringing the agreed SMS Messages interconnect into service.

The technical principles for the interconnection are detailed in the Service Schedules 01 and 02 to the BT SMS Messages Interconnect Agreement.

Discussions will be held between the OPERATOR and BT to establish; the proposed nature of the SMS Messages interconnect, the services and facilities that are required to interwork between the two networks, the physical locations of the interconnecting points, the physical realisation of the transmission links and the type and build level of the equipment to be connected between the Operator and BT networks.

The information required of both BT and the OPERATOR to adequately describe the initial SMS Messages interconnect required is set out in the Signalling Network Planning Document:

BT and the OPERATOR should provide the information using the Signalling Network Planning Document. The content and requirement of this document will be discussed during the early planning of the SMS Messages Interconnect.

The details contained within the completed Signalling Network Planning Document will form the agreed arrangements for the SMS Messages interconnection and, together with the appropriate Capacity Profile (Appendix 31a and/or Appendix 31b as appropriate) will be documented in the Technical Master Plan.

The parties will exchange Capacity Profiles and Capacity Orders. The format of this information and how it should be provided is detailed in Section 11.3 of this Manual.

The Technical Standards for the specification of Electrical and Physical Interfaces, Signalling and Transmission are shown in Appendix 1, 2 and 3 respectively in the Main Body of the BT SMS Messages Interconnect Agreement.

### 11.2.3.2	Provision of SMS Messages Interconnect Capacity

Once the OPERATOR and BT have signed the SMS Messages Interconnect Agreement and both BT and the OPERATOR has provided each other with the information contained within the Signalling Network Planning Document, BT or the OPERATOR may provide a formal order (Appendix 32a and/or Appendix 32b as appropriate) to the other for the provision of SMS Messages interconnect capacity.

The provision of new SS7 Signalling Circuit 2Mb/s Capacity is catered for jointly under the BT SMS Messages Interconnect Agreement (Service Schedule 01) and the BT Standard Interconnect Agreement. The provisioning activities are described for In-Span Interconnection in Section 4 and for Customer Sited Interconnection in Section 5 of this Provisioning Manual.

The procedures to fulfil orders for additions and changes to the SS7 Signalling Circuit 2Mb/s Capacity between the OPERATOR and BT are described in Sections 4 - 7 of this Provisioning Manual.

The provision of new SS7 MAP Signalling Link 64Kb/s Capacity is catered for under the BT SMS Messages Interconnect Agreement (Service Schedule 02. The provisioning activities are described Section 11.4 of this Provisioning Manual.

## 11.3. CAPACITY PROFILE

This section describes the procedures used to exchange capacity profile information between both the OPERATOR and BT and gives guidance on how the information should be presented. The requirements for Capacity profile information are set out in Paragraph 4 of Service Schedule 01 (2Mbit/s SS7 Signalling Interconnect Link) and Service Schedule 02 (64Kbit/s SS7 MAP Signalling Link) to the BT SMS Messages Interconnect Agreement.

Capacity Profiles for all existing and proposed Switch Connections shall be supplied by either the OPERATOR or BT in line with the content, periodicity and timescales specified in Paragraph 4 Service Schedule 01 (2Mbit/s SS7 Signalling Interconnect Link) and Service Schedule 02 (64Kbit/s SS7 MAP Signalling Link) to the BT SMS Messages Interconnect Agreement.

The Capacity Profile for Capacity Provision and Capacity Re-arrangement should be compiled using the form contained in Appendix 31a and/or Appendix 31b to this Manual. The forms are titled:

### APPENDIX 31a

12 Month SS7 Signalling Circuit 2Mbit/s Switch Port Capacity - Ordering Profile

### APPENDIX 31b

12 Month SS7 MAP Signalling Link (64Kbit/s) Switch Terminal Capacity - Ordering Profile

Explanatory notes to assist with the completion of the forms are provided.

Electronic templates can be supplied to the OPERATOR by your usual BT Network/Technical contact, or may be obtained from the BT web site, to enable the information to be supplied in electronic form, which is the preferred format.

The Capacity Profile should be sent by the OPERATOR to the BT Technical Account Manager, or by the BT Technical Account Manager to the OPERATOR, whichever is applicable.

The Key Stages and activities to be followed by the OPERATOR and BT in the Capacity Profile procedure are shown in Annex A.

## 11.4.	PROVISION OF SS7 MAP SIGNALLING LINK 64Kb/s CAPACITY

This section describes the provisioning activities required for the interconnection of new SS7 MAP Signalling Link 64Kb/s Capacity.

## 11.4.1	PROCEDURES AND TASK OVERVIEW

### 11.4.1.1 	Preliminary Planning

Demand for new SS7 MAP Signalling Link 64Kb/s Capacity will be identified by the BT or the OPERATOR at Technical Review Meetings.  Such demand, whether for augmentation of existing connections or for connections between new BT Switch Connections and/or new Operator Switch Connections, will be identified through Capacity Profiles and the Signalling Network Planning Document.

A number of technical issues (e.g. contained within the Signalling Network Planning Document) will require discussion at the Technical Review Meeting Forum prior to an order being placed.

### 11.4.1.2	Capacity Profile

Before placing Capacity Orders, the OPERATOR or BT will supply the other party with a Capacity Ordering Profile in relation to Capacity. Further information concerning Capacity Profile and Advance Capacity Order can he found in Section 11.3 of this Manual.

### 11.4.1.3	Capacity Orders

Orders will pass from the OPERATOR to the BT Technical Account Manager or from the BT Technical Account Manager to the OPERATOR. An example of an Order Form and explanatory notes are contained in Appendix 32b to this Manual.

The BT Technical Account Manager will liase with the OPERATOR to agree the Ready For Test (RFT) date and will deal with its agents within BT to plan the work necessary to fulfil the order.

Capacity Order time scales are contained in Paragraph 5.4 of Service Schedule 02 to the BT SMS Messages Interconnect Agreement.

### 11.4.1.4	Provision of SS7 MAP Signalling Link 64Kb/s Capacity

The Stages, Key Activities and Activity Descriptions for the provision of new SS7 MAP Signalling Link 64Kb/s are shown in Annex B.

### 11.4.1.5	Ready For Test

As soon as the capacity is ready for test, the OPERATOR and BT shall notify each other as such.

### 11.4.1.6	Operational Testing

Once the capacity has agreed RFT dates, a proposed test plan with dates for the capacity will be agreed between the OPERATOR and the BT Technical Account Manager for operational tests.

If the parties fail to agree an acceptable plan for the testing they should follow the disputes procedure referred to in Paragraph 5 of Service Schedule 02 to the BT SMS Messages Interconnect Agreement.

If either company cannot proceed with the test plan as scheduled a new plan mutually convenient to both companies will be agreed between the nominated operational people in both companies.

Please refer to section 11.4.2 for more information on testing requirements.

### 11.4.1.7	Bringing Into Service

When the appropriate operational testing has been completed satisfactorily the capacity will be left in an in an 'In Service' state, (also known as Ready For Service 'RFS').

At this point, for both: a). additional capacity on existing connections between BT Switch Connection to Operator Switch Connection and b). new capacity on new connections between BT Switch Connection to Operator Switch Connection, SMS Messages may be applied in both directions as appropriate.

Once the Ready For Service state is reached the capacity will then be supported jointly by BT and the OPERATOR.

## 11.4.2	Testing Requirements

Testing is performed to ensure that connection of capacity between the OPERATOR network and the BT network will not have adverse effects on the network and customers of either company.

Testing requirements for the first connection between the OPERATOR network and the BT network will consist of a combination of three activities, namely Interface Validation Testing (IVT), Network Interworking Tests (NIT) and Operational Testing (sometimes known as Circuit Acceptance Testing 'CAT'). The combination will depend on whether the proposed Switch Type / Build combination and Facilities to be used by either party have been connected to the other party’s network previously.

Testing of subsequent connections and additional capacity on existing connections are expected to require operational testing only, provided that the build and facilities have not changed since the previous capacity provision. However, the choice of switch, build and facilities for any new connections may affect the level of testing required.

The implications of the chosen switch and build level may be the subject of a specific technical meeting between the companies.

### 11.4.2.1	New Switch Testing Requirements

Note that with reference to section 11.4.1.6 in this Manual, the IVT and NIT requirement will need to have been completed to the satisfaction of both the OPERATOR and BT before the OPERATOR and BT switches can be for Operational Testing. The IVT / NIT arrangements will be organised by the TAM on behalf of the OPERATOR with BT’s Network Integration Facility 'NIF' if appropriate.

#### 11.4.2.1.1 	Full Testing

A new switch type not previously connected to the OPERATOR network or BT Network may require IVT using a protocol simulator, followed by NIT with a captive model and finally operational testing on the first connection.

At the discretion of the other party, externally generated IVT results may be accepted, as long as they are provided for scrutiny and have been completed with reference to the appropriate BSI specification.

#### 11.4.2.1.2 	Intermediate Level Testing

A new switch, of a type previously connected to the OPERATOR network or BT Network but with different facilities will require a scaled down NIT requirement followed by operational testing on the first traffic connection.

At the discretion of the other party, if the changes will not affect the SS7 interface, the NIT requirement may be waived, with or without the use of additional tests during the operational testing.

#### 11.4.2.1.3 	Reduced Testing

Switch types / build combinations which are known will require Operational testing on the first Traffic connection, provided that the functionality does not vary from those previously tested.

### 11.4.2.2	Time Scales

The provision of new SS7 MAP Signalling Link 64Kb/s is a joint undertaking between BT and the OPERATOR and timescales for commencement of Operational Testing are not prescribed within the BT SMS Messages Interconnect Agreement. However, both BT and the OPERATOR shall co-operated to ensure that testing requirements are completed at the earliest opportunity, but are subject to IVT and NIT requirements.

### 11.4.2.3.	Operational Interconnect Switch Testing

The operational testing phase is used to confirm that the switch data and network equipment of one party is suitable for connection to the network of the other party for customer services. In general, the operational testing phase will concentrate more on Service Types and the end to end customer service experience.

The requirements and procedures for operational testing are contained in the Operational Testing Manual Guide which is located at:

http://www.btwholesale.com/interconnect2bt/pstn_testing

## 11.5	CESSATION  OF SS7 MAP SIGNALLING LINK 64Kb/s CAPACITY

This section describes the provisioning activities required for the cessation of interconnect capacity on traffic routes between an OPERATOR switch and the BT network.

## 11.5.1  PROCEDURES AND TASK OVERVIEW

### 11.5.1.1 	Preliminary Planning

The need to cease capacity, as identified by analysis of SMS Message profile, will be discussed at the Technical Review Meeting Forum. As reductions in capacity may have an effect upon the operation of the SMS Message interconnect both companies should understand the changes  before orders are placed.

### 11.5.1.2	Orders for the Cessation of SS7 MAP Signalling Link (64Kb/s) Capacity

Orders will pass from the OPERATOR to the BT Technical Account Manager or from the BT Technical Account Manager to the OPERATOR. An example of an Order Form is set out with explanatory notes in Appendix 31b to this Manual. The BT Technical Account Manager will deal with its agents within BT to plan the work necessary to fulfil the order.

### 11.5.1.3	Cessation of Capacity

The Stages, Key Activities and Activity Descriptions for the Cessation of SS7 MAP Signalling Links (64Kb/s) are shown in Annex C.

## 11.5 DOCUMENT HISTORY

| ISSUE No. | DATE | AUTHOR | SUMMARY OF CHANGES |
| --- | --- | --- | --- |
| 1.0 | 04/02/2004 | Kevin Young | Initial issue |

# ANNEX A - STAGES AND KEY ACTIVITIES

## CAPACITY PROFILE PROCEDURE

### Key Activities - Descriptions

| Activity Name | Activity Descriptions | Owner |  |
| --- | --- | --- | --- |
| OPERATOR or BT provides Capacity Profile to the other | OPERATOR sends Capacity Profile to BT Technical Account Manager or BT Technical Account Manager sends Capacity profile to the OPERATOR | OPERATOR or BTWHOLESALE |  |
| Analysis of Capacity Profile | BT or the OPERATOR assesses the capability of its network to meet the Capacity Profile supplied by the other party. BT or the OPERATOR will seek clarification from the other party of any queries that arise from the assessment. | OPERATOR or BTWHOLESALE |  |
| Response to queries | The OPERATOR or BT responds to queries on the Capacity Profile raised by the other party. | OPERATOR or BTWHOLESALE |  |
| Parties agree the Capacity Profile | BT and the OPERATOR review each Capacity Profile at the relevant Technical Review Meeting. If it is agreed then the Profile is signed off by the authorised representatives of each party. | OPERATOR and BTWHOLESALE |  |
| OPERATOR or BT places Capacity Orders | The OPERATOR or BT places Capacity Orders against the Capacity Profile | OPERATOR and BTWHOLESALE |  |

# ANNEX B - STAGES AND KEY ACTIVITIES

## PROVISION OF SS7 MAP SIGNALLING LINK 64Kb/s CAPACITY

### Key Activities - Descriptions

| Activity Name | Activity Descriptions | Owner |
| --- | --- | --- |
| OPERATOR or BT sends Firm Order to the other | OPERATOR sends Capacity Order to BT | OPERATOR or BTWHOLESALE |
| Order validation | BT or the OPERATOR will validate the order against the agreed Capacity Profile in the Technical Master Plan. An invalid order will be passed back to the originator and will not be progressed. | OPERATOR or BTWHOLESALE |
| Schedule Test Dates | BT and the OPERATOR agree Operational Test Schedule for the order. | OPERATOR & BTWHOLESALE |
| Circuit Provision and Databuild | The 64Kbit/s SS7 MAP Signalling Links are provided and the data built. | OPERATOR & BTWHOLESALE |
| RFT notified | The 64Kbit/s SS7 MAP Signalling Links are notified as Ready For Test by both BT and the OPERATOR. | OPERATOR & BTWHOLESALE |
| Operational Testing | At the time when Operational Testing is due to start the testing teams in both BT and the OPERATOR will contact each other and then jointly carry out the Tests as specified in the relevant Operational Testing Manual. | OPERATOR & BTWHOLESALE |
| Bring Into Service | Subject to testing being completed satisfactorily both parties will confirm that the 64Kbit/s SS7 MAP Signalling Links are Ready for Service. Once the RFS has been confirmed the 64Kbit/s SS7 MAP Signalling Links will be available for introduction to public service. | OPERATOR & BTWHOLESALE |

END OF SECTION

# ANNEX C - STAGES AND KEY ACTIVITIES

## CESSATION OF CAPACITY

### Key Activities - Descriptions

| Activity Name | Activity Descriptions | Owner |
| --- | --- | --- |
| OPERATOR or BT sends Firm Order to the other | OPERATOR or BT sends Capacity Order to the other party. | OPERATOR or BTWHOLESALE |
| Order validation | The OPERATOR or BT will validate the order against the agreed Capacity Profile contained in the Technical Master Plan. An invalid order will be passed back to the originator and will not be progressed. | OPERATOR or BTWHOLESALE |
| Confirm that SMS Traffic removed | BT contacts the OPERATOR to confirm that traffic has been removed from the Interconnect circuit to be ceased. | OPERATOR & BTWHOLESALE |
| Cease Capacity | The capacity is ceased. | OPERATOR & BTWHOLESALE |
| Confirm Removal | When the SS7 MAP Signalling Link (64Kb/s) has been ceased the OPERATOR and BT will confirm completion | OPERATOR & BTWHOLESALE |

END OF SECTION